## Sheet1
Issue ID | Issue Summary | Severity | Assigned To | Date Raised | Target Resolution Date | Status | Resolution / Follow-up
ISS-001 | Checkout confirmation requirements need clarification | High | Project Manager | 2026-11-06 | 2026-11-09 | Open | Confirm expected behavior with the Business Owner
ISS-002 | Mobile layout requirements need more detail | Medium | UI/UX Designer | 2026-11-10 | 2026-11-13 | Open | Define supported screen sizes and review layouts
ISS-003 | Test environment may not be ready for testing | High | Developer | 2026-12-21 | 2026-12-22 | Open | Verify environment readiness before testing begins