## Sheet1
Milestone ID | Milestone Name | Planned Date | Actual Date | Status | Dependencies | Comments
M-001 | Requirements Finalized | 2026-11-06 |  | Not Started | Requirements gathering | Requires requirements review
M-002 | Project Scope Approved | 2026-11-10 |  | Not Started | Requirements finalized | Requires Business Owner approval
M-003 | UI/UX Design Approved | 2026-11-25 |  | Not Started | Design completed | Requires design review
M-004 | Core Development Completed | 2026-12-18 |  | Not Started | Product listing, accounts, cart, and checkout | Planned development completion
M-005 | Functional Testing Completed | 2026-12-24 |  | Not Started | Core development completed | Testing results must be reviewed
M-006 | Defects Fixed and Retested | 2026-12-30 |  | Not Started | Functional testing completed | Release-blocking defects should be resolved
M-007 | Release Readiness Reviewed | 2026-12-31 |  | Not Started | Testing and retesting | Requires release-readiness review
M-008 | Website Launch | 2027-01-04 |  | Not Started | Release readiness approved | Launch remains subject to approval
M-009 | Project Handover Completed | 2027-01-06 |  | Not Started | Website launch | Handover documentation and closure