## Sheet1
Task ID | Task Name | Planned Start | Planned Finish | Actual Start | Actual Finish | Progress (%) | Status | Variance / Comments
T-001 | Finalize project requirements | 2026-11-04 | 2026-11-06 |  |  | 0 | Not Started | Planned dates only; work has not started
T-002 | Approve project scope | 2026-11-09 | 2026-11-10 |  |  | 0 | Not Started | Awaiting scope review and approval
T-003 | Prepare UI/UX designs | 2026-11-17 | 2026-11-23 |  |  | 0 | Not Started | Planned design activity
T-004 | Review UI/UX designs | 2026-11-24 | 2026-11-25 |  |  | 0 | Not Started | Depends on completion of design work
T-005 | Develop product listing | 2026-11-26 | 2026-12-01 |  |  | 0 | Not Started | Planned development activity
T-006 | Develop user accounts | 2026-12-02 | 2026-12-07 |  |  | 0 | Not Started | Planned development activity
T-007 | Develop shopping cart | 2026-12-08 | 2026-12-11 |  |  | 0 | Not Started | Planned development activity
T-008 | Develop checkout | 2026-12-14 | 2026-12-18 |  |  | 0 | Not Started | Planned development activity
T-009 | Perform functional testing | 2026-12-21 | 2026-12-24 |  |  | 0 | Not Started | Testing planned after development
T-010 | Fix defects and retest | 2026-12-28 | 2026-12-30 |  |  | 0 | Not Started | Planned defect resolution
T-011 | Review release readiness | 2026-12-31 | 2026-12-31 |  |  | 0 | Not Started | Planned readiness review
T-012 | Launch website | 2027-01-04 | 2027-01-04 |  |  | 0 | Not Started | Subject to required approvals
T-013 | Complete project handover | 2027-01-05 | 2027-01-06 |  |  | 0 | Not Started | Planned project closure activity