## Sheet1
Metric | Current Value | Target / Expected Value | Status | Comments
Overall Project Status | Planning Complete | Ready for Execution | Planning | Execution has not started
Task Progress | 0% | 100% by planned closure | Not Started | All tasks remain planned
Schedule Status | Not Yet Measured | Complete within approved schedule | Pending | No actual progress data available
Budget Estimate | PKR 269,500 | Within approved budget | Pending | Illustrative estimate; not formally approved
Open Issues | 3 | Resolve high-priority issues before release | Monitoring | Three simulated issue examples are logged
High-Priority Risks | 5 | Reduce exposure through mitigation | Monitoring | Based on the initial risk register
Quality Readiness | Not Yet Tested | Required quality checks passed | Not Started | Testing has not started
Scope Changes | 3 Proposed | Review every request before implementation | Pending | Requests remain proposed