## Sheet1
Risk ID | Risk Description | Original Priority | Current Likelihood | Current Impact | Current Priority | Mitigation Progress | Owner | Status
R-001 | Development may take longer than planned | High | Medium | High | High | Not Started | Project Manager | Open
R-002 | Stakeholders may change requirements during development | High | Medium | High | High | Not Started | Project Manager | Open
R-003 | Critical defects may be discovered near launch | High | Medium | High | High | Not Started | SQA Tester | Open
R-004 | Key team member may become unavailable | Medium | Low | High | Medium | Not Started | Project Manager | Open
R-005 | Website performance may be poor under expected traffic | Medium | Medium | Medium | Medium | Not Started | Developer | Open
R-006 | Customer information may be exposed due to security weaknesses | High | Low | High | High | Not Started | Developer | Open
R-007 | Stakeholder feedback or approvals may be delayed | Medium | Medium | Medium | Medium | Not Started | Project Manager | Open
R-008 | Team may misunderstand a requirement | High | Medium | High | High | Not Started | Project Manager | Open