## Sheet1
Change ID | Date Recorded | Task / Milestone | Original Date | Revised Date | Reason for Change | Approved By | Status
SCH-001 | 2026-12-18 | Functional Testing Completed | 2026-12-24 | 2026-12-28 | Illustrative scenario: development delays require testing dates to be reviewed | Not Assigned | Proposed
SCH-002 | 2026-12-24 | Website Launch | 2027-01-04 | 2027-01-07 | Illustrative scenario: additional time may be needed for defect verification | Not Assigned | Proposed