## Sheet1
Communication Activity | Purpose | Audience | Frequency | Method | Owner
Project Status Update | Share progress, completed tasks, and upcoming work | Business Owner and Project Team | Weekly | Email or project status report | Project Manager
Requirements Review | Confirm requirements and resolve questions | Business Owner, Designer, Developer, SQA Tester | At key planning milestones | Meeting or shared document | Project Manager
Design Review | Collect feedback and obtain design approval | Business Owner, Designer, Developer | At design milestones | Design review meeting | Project Manager
Development Progress Review | Identify progress, blockers, and delays | Project Manager and Development Team | Weekly | Team meeting or project tracker | Project Manager
Testing and Defect Updates | Share test results, defects, and retesting progress | Project Manager, Developer, Business Owner | Throughout testing | Defect log or email | SQA Tester
Risk Review | Review project risks and mitigation actions | Project Manager and Business Owner | Weekly | Shared risk register | Project Manager
Release Readiness Review | Confirm testing completion and launch readiness | Project Manager, Developer, SQA Tester, Business Owner | Before launch | Review meeting | Project Manager
Project Closure Summary | Summarize deliverables, outcomes, and outstanding items | Business Owner and Project Team | At project closure | Closure report | Project Manager