## Sheet1
Task / Deliverable | Project Manager | UI/UX Designer | Developer | SQA Tester | Business Owner
Confirm project scope | R | C | C | C | A
Gather requirements | R | C | C | C | A
Create project schedule | A | I | C | I | I
Design website screens | C | R | C | C | A
Review and approve design | C | R | C | I | A
Develop product listing and accounts | I | C | A | C | I
Develop shopping cart and checkout | I | C | A | C | I
Perform functional testing | C | I | C | R | A
Fix defects and retest | I | C | R | A | I
Review release readiness | R | I | C | C | A
Approve website launch | R | I | C | C | A
Complete project handover and closure | A | I | C | C | C
RACI stands for:
R — Responsible: The person who performs the work.
A — Accountable: The person ultimately answerable for the result.
C — Consulted: Someone whose input is needed.
I — Informed: Someone who needs updates.