## Sheet1
Risk ID | Risk Description | Likelihood | Impact | Priority | Mitigation Plan | Status
R-001 | Development may take longer than planned. | Medium | High | High | Break work into smaller tasks, review progress regularly, and address blockers early. | Open
R-002 | Stakeholders may change requirements during development. | Medium | High | High | Confirm requirements early and assess the schedule and scope impact of requested changes. | Open
R-003 | Critical defects may be discovered near the planned launch. | Medium | High | High | Test features throughout development and reserve time for defect fixing and retesting. | Open
R-004 | A key team member may become unavailable. | Low | High | Medium | Document important work and identify backup support where possible. | Open
R-005 | Website performance may be poor under expected traffic. | Medium | Medium | Medium | Define performance targets and conduct performance testing before launch. | Open
R-006 | Customer information may be exposed due to security weaknesses. | Low | High | High | Apply appropriate security controls and conduct security checks before launch. | Open
R-007 | Stakeholder feedback or approvals may be delayed. | Medium | Medium | Medium | Agree on review deadlines and follow up on pending decisions. | Open
R-008 | The team may misunderstand a requirement. | Medium | High | High | Review requirements with stakeholders and use clear acceptance criteria. | Open