## Sheet1
WBS ID | Project Phase | Task Name | Task Description
1 | Project Initiation | Project Setup | Define the project purpose, objectives, and initial scope.
1.1 | Project Initiation | Identify Stakeholders | Identify the business owner, project manager, designer, developers, tester, and customers.
2 | Project Planning | Gather Requirements | Identify and document the website's functional and non-functional requirements.
2.1 | Project Planning | Define Project Scope | Confirm included features, excluded features, and project boundaries.
2.2 | Project Planning | Create Project Schedule | Estimate task durations, dependencies, and milestones.
2.3 | Project Planning | Identify Project Risks | Document potential risks and planned responses.
3 | Design | UI/UX Design | Create wireframes and visual designs for the website.
3.1 | Design | Review Design | Get stakeholder feedback and approval for the proposed design.
4 | Development | Develop Product Listing | Build the product listing and product details features.
4.1 | Development | Develop User Accounts | Build registration and login functionality.
4.2 | Development | Develop Shopping Cart | Build add, update, and remove cart item functionality.
4.3 | Development | Develop Checkout | Build checkout, order submission, and confirmation features.
5 | Testing | Functional Testing | Test the agreed website features against requirements.
5.1 | Testing | Defect Fixing and Retesting | Track defects, coordinate fixes, and retest corrected features.
6 | Launch Preparation | Release Readiness Review | Check whether agreed acceptance criteria have been met.
6.1 | Launch Preparation | Website Launch | Coordinate the planned release after required approvals.
7 | Project Closure | Project Handover and Closure | Prepare the final report, handover information, and lessons learned.