## Sheet1
Change ID | Related Request ID | Approved Change | Decision Date | Implementation Owner | Implementation Status | Verification Notes
CH-001 | CR-001 | Add product search feature | 2026-11-11 | Developer | Pending Approval | Implementation must not begin until formal approval is recorded
CH-002 | CR-002 | Add wishlist feature | 2026-11-13 | Developer | On Hold | Awaiting impact assessment and scope approval
CH-003 | CR-003 | Improve mobile responsiveness | 2026-11-17 | UI/UX Designer | Pending Approval | Review responsive design requirements before implementation