## Sheet1
Decision ID | Decision Date | Decision Description | Reason | Decision Owner | Status
DEC-001 | 2026-11-02 | Use a web-based e-commerce platform for the initial release | Focus on the core shopping experience and avoid expanding scope to native mobile apps | Business Owner | Proposed
DEC-002 | 2026-11-06 | Require review of scope changes before implementation | Prevent uncontrolled scope growth and assess schedule impact | Project Manager | Proposed
DEC-003 | 2026-11-10 | Complete UI/UX review before development begins | Reduce design-related rework during development | Business Owner | Proposed
DEC-004 | 2026-11-16 | Reserve time for defect fixing and retesting | Allow the team to address defects before the planned release | Project Manager | Proposed
DEC-005 | 2026-12-31 | Require release-readiness review before launch | Confirm testing results and outstanding issues before release | Business Owner | Proposed