## Sheet1
Issue ID | Issue Description | Date Identified | Impact | Priority | Assigned To | Action Plan | Status
Issue ID | Issue Description | Date Identified | Impact | Priority | Assigned To | Action Plan | Status
ISS-001 | Checkout requirements are missing a clear order confirmation rule | 2026-11-06 | May cause inconsistent checkout behavior | High | Project Manager | Confirm the expected confirmation behavior with the Business Owner | Open
ISS-002 | Mobile layout requirements are not specific enough | 2026-11-10 | May lead to inconsistent mobile design | Medium | UI/UX Designer | Define supported screen sizes and review responsive layouts | Open
ISS-003 | Test environment is not ready when testing is scheduled | 2026-12-21 | May delay functional testing | High | Developer | Prepare and verify the test environment before testing starts | Open