## Sheet1
Task ID | Task Name | Assigned Role | Priority | Start Date | Due Date | Status | Comments
T-001 | Finalize project requirements | Project Manager | High | 2026-11-04 | 2026-11-06 | Not Started | Confirm requirements with the business owner
T-002 | Approve project scope | Business Owner | High | 2026-11-09 | 2026-11-10 | Not Started | Review and approve the scope document
T-003 | Prepare UI/UX designs | UI/UX Designer | High | 2026-11-17 | 2026-11-23 | Not Started | Create website screens and user flows
T-004 | Review UI/UX designs | Project Manager | Medium | 2026-11-24 | 2026-11-25 | Not Started | Collect feedback and obtain approval
T-005 | Develop product listing | Developer | High | 2026-11-26 | 2026-12-01 | Not Started | Build product listing and detail pages
T-006 | Develop user accounts | Developer | High | 2026-12-02 | 2026-12-07 | Not Started | Implement registration and login
T-007 | Develop shopping cart | Developer | High | 2026-12-08 | 2026-12-11 | Not Started | Implement add, update, and remove cart items
T-008 | Develop checkout | Developer | High | 2026-12-14 | 2026-12-18 | Not Started | Implement checkout and order placement
T-009 | Perform functional testing | SQA Tester | High | 2026-12-21 | 2026-12-24 | Not Started | Test agreed requirements and record defects
T-010 | Fix defects and retest | Developer / SQA Tester | High | 2026-12-28 | 2026-12-30 | Not Started | Fix reported defects and verify fixes
T-011 | Review release readiness | Project Manager | High | 2026-12-31 | 2026-12-31 | Not Started | Check testing results and outstanding issues
T-012 | Launch website | Developer / Business Owner | High | 2027-01-04 | 2027-01-04 | Not Started | Release after required approvals
T-013 | Complete project handover | Project Manager | Medium | 2027-01-05 | 2027-01-06 | Not Started | Document handover and close the project